DRAFT CONTRACT

PART 2

CONTRACT PROVISIONS

- TABLE OF CONTENTS

TABLE OF CONTENTS	1

1	Introduction	5

1.1	General information	5

1.2	Purpose of the procurement	5

1.3	Precedence of documents	5

2	Scope of Delivery	5

2.1	Test and verification	5

3	Terms of delivery	6

4	System responsibility	6

5	Transfer of risk	6

6	Title to the Scope of Delivery	6

7	Intellectual property rights	6

7.1	The Purchaser’s general right of use	6

7.2	Communication of information and documentation to third parties	7

7.3	The Contractor’s responsibility for third party rights	7

7.4	Third-party claims	7

8	Subcontractors	8

9	Changes to the Contract	8

9.1	General information	8

9.2	Changing the Contract using a Change Order	8

10	Right to demand access to information and inspections	9

11	Cost control	9

12	Quality assurance and configuration management	10

12.1	Quality assurance	10

12.2	Procedure for handling deviations	10

13	Confidentiality and classified information	10

13.1	Confidentiality	10

13.2	Classified information	11

14	Warranty	11

14.1	Scope of the warranty	11

14.2	Warranty period	11

14.3	Rectification	12

15	Breach of contract on the part of the Contractor	12

15.1	Breach of contract	12

15.2	Duty to provide information in the event of delays	12

15.3	Purchaser’s sanctions in the event of breach of contract	13

15.4	Anticipatory breach of contract	14

16	Breach of contract on the part of the Purchaser	15

16.1	Breach of contract	15

16.2	Duty of notification	15

16.3	Adjustment of price and progress	15

16.4	The Contractor’s sanctions in the event of breach of contract	15

17	The Contractor’s Corporate Social Responsibility	15

18	Indemnification	16

18.1	Indemnification by the Contractor	16

18.2	Indemnification by the Purchaser	16

18.3	Notification of claims	16

19	Purchaser’s right of cancellation	16

20	Force majeure	17

20.1	General information	17

20.2	Impact on costs and schedule	17

20.3	Cancellation for convenience	17

21	Miscellaneous provisions	17

21.1	Communication	17

21.2	Duty to provide information	17

21.3	Visiting procedures	18

21.4	Insurance	18

21.5	Transfer of claims	18

22	Disputes and choice of law	18

23	Entry into force	18

# List of annexes:

|  | Annex A Scope of Delivery |  |
| --- | --- | --- |
|  | Annex B Price and Payment Conditions |  |
|  | Annex C Time and Terms of Delivery |  |
|  | Annex D Points of Contact |  |
|  | Annex E Specifications |  |
|  |  | Annex E-0 System Design Description |
|  |  | Annex E-1 System Segment Specification |
|  |  | Annex E-2 Logistic Support Specification |
|  |  | Annex E-3 Materiel Data |
|  |  | Annex E-3, Appendix A (Codification) Contract Clause – Form 5054 |
|  |  | Annex E-3, Appendix B Parts Identification Form (PIF) – Form 5056 |
|  | Annexes G, H, I, J, K – not applicable |  |
|  | Annex L Norwegian Defence Material Agency’s Ethical Requirements |  |
|  | Annex M Standard forms |  |
|  |  | Annex M-1 General Terms for Cost Control |
|  |  | Annex M-2 Specification of Price |
|  |  | Annex M-3 Request for Change |
|  |  | Annex M-4 Change Order |
|  |  | Annex M-5 – not applicable |
|  |  | Annex M-6 Supplemental Agreement |
|  |  | Annex M-7 Certificate of Conformity |
|  |  | Annex M-8 Request for Acceptance of Deviation Permit / Concession |
|  | Annexes N, O, P – not applicable |  |
|  | Annex Q Contractor’s Solution Description |  |

Introduction

General information

The Purchaser and the Contractor are jointly referred to as ‘the Parties’ and individually as ‘the Party’.

Purpose of the procurement

The purpose of this procurement is to meet the Norwegian Armed Forces’ need for
The Test & Verification section are increasing their meteorological capacity by procuring mobile/ portable meteorological sounding system suited for measuring weather conditions during artillery/ mortar ammunition testing.

Precedence of documents

In the event of conflict between the provisions of the contract documents, the following order of precedence shall apply:

- Signed Contract and Contract Provisions

- Annex A Scope of Delivery

- Annex B Price and Payment Conditions

- Annex C Time and Terms of Delivery

- Annex E Specifications

- Annex L Norwegian Defence Material Agency’s Ethical Requirements

- Other annexes

- Annex Q Contractor’s Solution Description

If technical specifications contain both drawings or other illustrations and text, the text shall take precedence.

Scope of Delivery

The Contractor shall deliver the Scope of Delivery as defined in Annex A Scope of Delivery and further specified in:

- Annex E Specifications

Test and verification

In order to verify that the requirements of Annex E Specifications are met, the Contractor shall carry out verification in accordance with the verification procedures set out in Annex E Specifications. Verification procedures, such as testing, analysis and inspection, are described in Annex E Specifications.

The Contractor remains fully liable for the fulfilment of all its obligations under this Contract regardless of whether the Purchaser has provided support in connection with or participated in the Contractor’s performance of the Contract. This means, among other things, that any support or participation on the part of the Purchaser in the form of approval, acceptance or similar confirmation during the design, manufacture, testing, verification and delivery does not relieve the Contractor of any of its obligations.

Terms of delivery

The delivery shall meet all the requirements set out in the Contract at the time of delivery. All deliveries shall be new, and, where relevant, cleaned, and equipped with all necessary certificates.

All deliveries shall be free of encumbrances or claims of any kind at the time of delivery.

The Contractor shall deliver the Scope of Delivery in accordance with the times and terms of delivery defined in Annex C Time and Terms of Delivery.

System responsibility

The Contractor shall have system responsibility for the Scope of Delivery. This entails overall responsibility for the planning, design, development and integration of the Scope of Delivery in order to ensure that it is fully functional and meets the requirements of the Contract.

Where the Scope of Delivery is part of a system or one or more subsystems, the Contractor is responsible for ensuring that the Scope of Delivery does not have a negative impact on the systems so that they do not work as intended or are not fully functional.

Subsystems include, but are not limited to, Provided Items, spare parts, special tools and test equipment.

Transfer of risk

The risk associated with the Scope of Delivery is transferred to the Purchaser upon delivery in accordance with Incoterms as agreed in Annex C Time and Terms of Delivery.

Title to the Scope of Delivery

The Scope of Delivery becomes the property of the Purchaser from the time it is delivered in accordance with Annex C. The transfer of title means that the Purchaser acquires full actual and legal rights to the Scope of Delivery.

Intellectual property rights

The Purchaser’s general right of use

The Purchaser is granted a worldwide, non-exclusive, perpetual, unrestricted and free right to any form of use of all technology, software, other intellectual property rights, information and documentation (hereinafter collectively referred to as ‘the Technology’) delivered in accordance with the Contract. The Technology includes, but is not limited to, user manuals, maintenance documentation, drawings, Materiel Data and lists of spare parts.

The Purchaser shall receive, in a format suitable for the Purchaser, all relevant information and documentation to enable the Purchaser to make full use of the Technology.

Where relevant, the Contractor shall also deliver interface documentation that describes:

- General form, fit and function

- Information needed for installation, operation, maintenance and training

- Changes to and corrections of technical documentation delivered by the Purchaser to the Contractor

The Purchaser may, at its own expense, freely use, copy, transfer, modify or further develop the Technology for internal use in all parts of the Norwegian Armed Forces in any manner it deems expedient.

Communication of information and documentation to third parties

Information and documentation delivered under the Contract that are specified as or deemed to be confidential information shall not be disclosed to third parties without the Contractor’s written consent.

Subject to written consent, the Purchaser may disclose confidential information and documentation received under the Contract to third parties assisting the Purchaser, including in connection with procurements etc. If the Purchaser so requests, the Contractor shall assist the Purchaser with this. The Purchaser shall cover any direct costs incurred by the Contractor as a result of such assistance. If the information or documentation is deemed to constitute trade secrets and the Contractor so requests, the recipient shall sign the Purchaser’s declaration of confidentiality.

During military operations or exercises, the Purchaser is free to transfer all information and documentation to the Norwegian Armed Forces’ coalition countries without such a declaration of confidentiality, if such transfer is deemed necessary for the performance of the military operation or exercise.

The Contractor’s responsibility for third party rights

The Contractor guarantees and shall ensure that:

- The Contractor is entitled to grant the Purchaser the agreed rights to the Technology and everything else covered by the Contract;

- Neither the Technology nor anything else covered by the Contract, or the Purchaser’s use of this, violates third-party intellectual property rights, other rights or legally protected interests.

The Contractor shall indemnify the Purchaser for all and any claims from third parties, including covering the Purchaser’s losses, costs and damage arising from the Contractor’s breach or non-fulfilment of the above-mentioned guarantee.

A defect in title is deemed to exist if the Technology violates third-party rights.

Third-party claims

If a third party claims that the Technology or anything else covered by the Contract and/or the Scope of Delivery violates third-party rights, the Parties shall notify each other without undue delay. The Contractor shall deal with third-party claims for its own account in cases where the Contractor has violated third-party rights.

The Contractor shall initiate and perform the work on remedying the situation without undue delay by:

- ensuring that the Purchaser can use the delivery as before without violating third-party rights, or

- making a corresponding and, to the Purchaser, equivalent delivery that does not violate third-party rights.

Subcontractors

The Contractor may not assign material parts of the work relating to the Scope of Delivery to subcontractors, or replace an identified subcontractor, without the Purchaser’s prior written consent.

The Contractor remains fully responsible for the fulfilment of all its obligations under the Contract, regardless of whether the Contractor has subcontracted any parts of the work.

The Contractor shall convey all necessary terms and conditions under this Contract to subcontractors to ensure that the Purchaser has the same rights under subcontracts as under the Contract. Particular emphasis shall be placed on the Norwegian Defence Materiel Agency’s ethical requirements for contractors, and on health, safety and the environment, quality assurance, right of access to information and the duty of confidentiality.

Changes to the Contract

General information

The terms and conditions of the Contract can only be changed if the Parties sign a Supplemental Agreement using Annex M-6 or if the Purchaser issues a Change Order using Annex M-4. The Contractor may propose changes to the Contract using form M-3 Request for Change.

Neither the Contractor nor the Purchaser may invoke any statements, omissions or acts, including minutes of meetings or correspondence, as constituting valid changes to the Contract.

The terms and conditions of the Contract shall also apply to any changes, unless otherwise explicitly stated in the Supplemental Agreement or Change Order.

Changing the Contract using a Change Order

The Purchaser may at all times make changes to the Contract using Annex M-4 Change Order, insofar as such changes fall within the scope of what the Parties could reasonably have expected when the Contract was entered into.

When the Purchaser has issued a Change Order, the Contractor shall immediately commence work in accordance with the Change Order, even if the consequences of the Change Order have not yet been determined.

When a Change Order is issued, the Contractor may be entitled to a deadline extension and/or a price adjustment.

If the Contractor wishes to request an extension of the deadline or price adjustment, notification must be given within 14 calendar days of receipt of the Change Order. The right to a deadline extension and/or price adjustment lapses if notification is not given by the deadline.

The deadline extension shall reflect the actual effect of the change on progress. The Contractor shall document the effect in writing and keep the Purchaser continuously up to date.

A price adjustment shall be based on prices agreed in the Contract or on cost control, cf. Clause 12.

A specified request for a deadline extension and/or price adjustment shall be submitted to the Purchaser as soon as it is possible to ascertain the consequences. Once agreement has been reached on the consequences for the progress and price adjustment, this shall be formalised in a Supplemental Agreement.

If agreement is not reached, the Purchaser shall, when endorsing the Change Order, grant the Contractor such compensation or deadline adjustment as the Purchaser believes the Contractor is entitled to. If the Contractor has not initiated legal steps pursuant to Clause 23 Disputes and choice of law within six months of the Purchaser’s endorsement, settlement for the performance of the change work shall be deemed to have been finally agreed.

Notified breach of contract pursuant to Clause 17 Breach of contract on the part of the Purchaser shall follow a corresponding process. The deadline for giving notice of a deadline extension or price adjustment runs from the day on which the Contractor gives notice of the breach of contract.

Right to demand access to information and inspections

The Purchaser may demand access to the Contractor’s documents or to conduct inspections of the Contractor’s premises. Such access or inspections may be necessary in order to perform or verify quality assurance, cost control, contractor assessment, requirements regarding production and working conditions, security clearance, or progress under the Contract.

The Contractor shall, at the Purchaser’s request, grant personnel appointed by the Purchaser access to all information and documents that the Purchaser considers necessary. Furthermore, the Contractor shall grant access to relevant personnel, production equipment and premises when this is necessary for the Purchaser to be able to perform its assignment. The Purchaser may also demand access to the Contractor’s accounts if there is suspicion of financial irregularities or similar.

Cost control

The Contractor shall grant the Purchaser’s regulatory agency, cf. Annex D Points of Contact, access to cost control in the following cases:

- Any changes to the Scope of Delivery, such as reductions, expansions, extensions or additional deliveries not already priced in the Contract,

- Exercise of options not priced in the Contract,

- Termination and/or cancellation of the Contract in whole or in part.

Cost control shall be carried out in accordance with Annex M-2 Specification of Price and Annex M-1 General Terms for Cost Control.

Quality assurance and configuration management

Quality assurance

The Contractor’s quality assurance system shall meet the requirements of ISO 9001.

Procedure for handling deviations

If the Contractor wishes to deliver a limited number of units that deviate from the requirements in the Contract or from the agreed baseline, the Contractor shall apply for a deviation permit, cf. Annex M-8 Request for Acceptance of Deviation Permit/Concession.

The Contractor shall sign Certificate of Conformity (CoC), Bl 5357 E, to state that the products provided fully comply with the contractual requirements.

Customer approved Deviation permit, or concession, are the only exception allowed and shall be listed on the CoC, block 5.

The Contractor shall distribute the signed CoC, Bl 5359 E with the delivery of the product. CoC to be archived by the Contractor.

The Contractor shall sign Certificate of Conformity (CoC), Bl 5359 E, to state that the products provided fully comply with the contractual requirements.

Confidentiality and classified information

Confidentiality

Any information that the Parties become aware of in connection with this Contract and the performance thereof shall be treated as confidential and shall not be disclosed to any third parties without the consent of the other Party.

The Purchaser’s duty of confidentiality under this provision is not more extensive than what follows from the Act of 10 February 1967 relating to procedure in cases concerning the public administration (the Public Administration Act) or the Act of 19 May 2006 relating to the right of access to documents held by public authorities and public undertakings (the Freedom of Information Act). The Contractor shall be notified before such information is disclosed.

The duty of confidentiality is not an obstacle to the information being used when no legitimate interest indicates that it should be kept secret, for example if it is in the public domain or publicly available elsewhere.

The Parties shall take all necessary precautions to prevent unauthorised persons from gaining access to or knowledge of confidential information.

The duty of confidentiality shall apply to the Parties’ employees and subcontractors and to third parties acting on behalf of the Parties in connection with the performance of the Contract. The Parties may only disclose confidential information to subcontractors and third parties to the extent necessary for performance of the Contract, and provided that they are subject to a duty of confidentiality corresponding to this provision.

The duty of confidentiality shall not prevent the Parties from utilising the experience and expertise acquired in connection with performance of the Contract.

The duty of confidentiality also applies after the Contract has expired. Employees or others who leave their position with either of the Parties shall continue to be bound by a duty of confidentiality in relation to the above-mentioned matters also after they have left. The duty of confidentiality ceases to apply five years after the day of the last delivery, unless otherwise provided for in laws or regulations.

The Parties shall obtain prior approval if information about the Contract is to be made known to the public for promotional or other purposes.

Classified information

Separate rules apply to information that is classified pursuant to the Security Act and its regulations, and the Contractor and any subcontractors and its employees that will have access to such information are obliged to familiarise themselves with these rules. A security agreement shall be established through the competent security authority if the Contractor and/or subcontractors are to process classified information.

Warranty

Scope of the warranty

The Contractor guarantees that all deliveries will be in accordance with all requirements in the Contract throughout the warranty period specified in Clause 15.2 Warranty period. This means, among other things, that if a fault or defect in functionality or quality arises during the warranty period, it shall be rectified by the Contractor for the Contractor’s account.

Faults and defects caused by normal wear and tear are not covered by the warranty. The same applies to faults or defects caused by incorrect use, storage or maintenance on the part of the Purchaser. These limitations do not apply if the Purchaser complies with the maintenance and operating instructions provided by the Contractor. The burden of proof is on the Contractor if the Contractor wishes to claim that non-fulfilment of the Contract is caused by the Purchaser.

Warranty period

The warranty is valid for two (2) years from the date of each delivery.

The warranty period is suspended for all parts that cannot be used for their purpose due to a fault or defect covered by the warranty. The suspension lasts until the matter has been rectified.

A warranty period of at least 12 months after rectification has been completed shall apply to the replaced or repaired parts or systems and the performance of the rectification work.

The Purchaser shall submit any complaints to the Contractor in writing within a reasonable time after becoming aware of the defect.

The above-mentioned deadlines do not apply if the Contractor has acted with gross negligence or contrary to honesty and good faith.

Rectification

If a fault or defect exists that is covered by the warranty, the Contractor shall rectify the fault or defect, including all parts damaged as a result of the fault or defect. The Contractor shall cover all costs relating to the rectification and shall initiate rectification without undue delay.

The Purchaser may demand changed or new acceptance tests and/or procedures to qualify or re-qualify the rectified Scope of Delivery for the Contractor’s account in order to ensure fulfilment of the Contract. The Purchaser is entitled to participate as an observer during any rectification work.

If the Contractor, without reasonable grounds, fails or refuses to initiate rectification as described above, or if it is essential that rectification takes place sooner than is possible for the Contractor to perform it, the Purchaser may carry out the work itself or assign it to someone else. The Purchaser shall not under any circumstances initiate such work until 14 calendar days have elapsed since the Contractor was notified in writing. The Contractor shall cover all costs in connection with rectification carried out by the Purchaser or its assignee, unless the Purchaser or its assignee has failed to rectify the defect in a satisfactory manner.

The Contractor is obliged to immediately hand over all necessary information and the right to use such information to the Purchaser, including to a third party acting on behalf of the Purchaser, in order to enable the Purchaser to exercise its rights pursuant to this clause.

Breach of contract on the part of the Contractor

Breach of contract

Breach of contract is deemed to exist if the Contractor fails to fulfil its obligations under the Contract and this is not due to circumstances caused by the Purchaser. The burden of proof is on the Contractor if the Contractor wishes to claim that non-fulfilment of the Contract was caused by the Purchaser.

Duty to provide information in the event of delays

If the Contractor has reason to believe that it will be unable to meet milestones or other provisions set out in Annex C Time and Terms of Delivery, the Contractor shall inform the Purchaser of this in writing without undue delay.

The Contractor shall, without undue delay, also inform the Purchaser of the cause of and duration of the delay, any effects it will have on other milestones and what measures the Contractor plans to implement to avoid, recover or limit the delay. If the Purchaser has comments on the proposed measures, the Purchaser shall inform the Contractor of this within a reasonable time. The Purchaser may instruct the Contractor to implement further measures if the Purchaser deems the proposed measures to be inadequate or otherwise inexpedient.

If the notified delay is not caused by the Purchaser, the Contractor is responsible for the delay and shall take any action necessary to avoid, recover or limit the delay.

Purchaser’s sanctions in the event of breach of contract

Withholding payment

In the event of breach of contract, the Purchaser may withhold payment to secure the Purchaser’s claims arising from the breach of contract. The amount withheld must be proportionate to the breach of contract.

The Purchaser’s right to reject defective deliveries

In the event of a defect, the Purchaser may reject the defective part of the delivery and any parts of the delivery that cannot be used as intended. Rejection must be given in writing. Rejected deliveries are deemed not to have been delivered.

Liquidated damages in the event of delays

If the deadlines stipulated in Annex C Time and Terms of Delivery are not met, a delay is deemed to exist on the part of the Contractor that entitles the Purchaser to liquidated damages.

Liquidated damages accrue automatically. Liquidated damages shall amount to 0.1% of the value of the delayed delivery and all other parts of the Scope of Delivery that cannot be used as intended due to the delay, for each calendar day the delivery is delayed. Liquidated damages are limited to 100 calendar days for each delayed part. The amount falls due for payment when the liquidated damages period expires and will be deducted from the final invoice. The Purchaser shall send a statement of liquidated damages to the Contractor.

Liquidated damages are regarded as final compensation for the delay, unless the delay exceeds 100 calendar days or the Contractor has acted with gross negligence. After 100 calendar days, the Purchaser can claim compensation for its financial loss, cf. Clause 16.3.5.

Price reduction

If the Contractor fails to remedy a breach of contract without undue delay, or by the agreed deadline, or is unable to remedy the breach of contract, the Purchaser may demand a price reduction.

The price reduction shall compensate for the reduced value of the delivery and shall be independent of any compensation paid. The price reduction shall not be less than the Contractor’s savings resulting from the work not being in compliance with the Contract.

Compensation

The Purchaser may claim compensation for any losses, including losses caused by additional work or other costs relating to breach of contract by the Contractor.

Compensation may not be claimed for indirect losses. Indirect losses include, but are not limited to, loss of profit of any kind, lost savings, loss of data and third-party claims. Loss of data is considered to be an indirect loss, unless the loss was caused by data processing that is the Contractor’s responsibility under the Contract.

The Contractor’s maximum liability in damages as a result of faults and defects under the Contract shall be limited to the Purchaser’s maximum obligation. This limitation of liability also applies if the Contract is terminated.

The above-mentioned limitation also applies in the event of negligence, but not in cases where the Contractor or a party for whom the Contractor is responsible has acted with gross negligence or intent.

Termination

Termination due to breach of contract

If the Contractor is in material breach of the Contract, the Purchaser may, after giving the Contractor written notice and a reasonable deadline to remedy the matter, terminate the Contract with immediate effect. The Contract can be terminated in whole or in part with future or retroactive effect.

The following shall always be deemed to constitute material breach of contract:

- Liquidated damages accrue to their maximum limit, or upon the expiry of an extended deadline if this expires later, or

- A defect in title that is not remedied in a satisfactory manner within a reasonable time, and that is material to the Purchaser, or

- The Contractor is in breach of the security agreement between the Parties, or

- The Contractor has been convicted of participation in or trading with a criminal organisation, corruption, fraud, money laundering, or a criminal offence relating to its professional conduct, and the judgment is final and enforceable, or

- The Contractor’s enterprise enters into debt settlement or compulsory liquidation proceedings, or

- The Contractor’s enterprise is wound up, suspended or is undergoing a corresponding process under applicable law.

Repeated non-material breaches on the part of the Contractor can also be deemed to collectively constitute material breach of contract.

If the Purchaser terminates the Contract for an individual delivery, it may at the same time terminate the Contract for deliveries already made or future deliveries if, because the deliveries are interdependent, they cannot be used for the purpose intended by the Parties at the time when the Contract was entered into.

Consequences of termination

Upon receiving notice of termination, both Parties shall immediately suspend their performance of the Contract and instruct all their subcontractors to do the same. However, the Parties and their subcontractors shall complete or secure work as necessary in order to avoid damage to property or injury to personnel.

Anticipatory breach of contract

If it is clear before the time of fulfilment that a breach of contract will occur that will entitle the Purchaser to terminate the Contract, the Purchaser is entitled to terminate the purchase before the time of fulfilment. Termination can be avoided if the Contractor immediately furnishes adequate assurance that the purchase will be completed.

When time allows, the Purchaser shall notify the Contractor so that it is given a chance to furnish assurance to avoid termination.

Breach of contract on the part of the Purchaser

Breach of contract

Breach of contract is deemed to exist if the Purchaser does not fulfil all its obligations under the Contract and this is not due to circumstances caused by the Contractor. The burden of proof is on the Purchaser if the Purchaser wishes to claim that non-fulfilment of the Contract was caused by the Contractor.

Duty of notification

The Contractor shall give the Purchaser written notification within a reasonable time after the breach of contract was or should have been discovered. If notification is not given within a reasonable time, the Contractor will forfeit its right to file a claim in connection with the breach of contract.

Adjustment of price and progress

If the notified breach of contract is caused by the Purchaser, and the breach of contract affects the performance of the Contract, the Contractor may demand a deadline extension and/or price adjustment. This shall take place in accordance with Clause 10.2 Changing the Contract using a Change Order. The Contractor is not entitled to any such adjustment if the delay or its consequences could have been avoided, recovered or limited had the Contractor fulfilled all its obligations under the Contract.

The Contractor’s sanctions in the event of breach of contract

Suspension of performance

The Contractor may not suspend its performance as a result of breach of contract on the part of the Purchaser, unless the breach is material.

Termination

In the event of material breach of contract, the Contractor can send written notification to the Purchaser that the Contract will be terminated unless the breach is remedied within 60 calendar days of receipt of the notification.

Compensation

The Contractor may claim compensation for all direct losses that can reasonably be attributed to the Purchaser’s breach of contract.

Compensation may not be claimed for indirect losses. Loss of data is considered to be an indirect loss.

The above-mentioned limitations of liability do not apply in cases where the Purchaser or a party for whom the Purchaser is responsible has acted with gross negligence or intent.

The Contractor’s Corporate Social Responsibility

The Contractor shall meet requirements for corporate social responsibility as defined in Annex L Norwegian Defence Materiel Agency’s Ethical Requirements. In the event of breach of these requirements, the Purchaser may invoke sanctions set out in Annex L Norwegian Defence Materiel Agency’s Ethical Requirements.

Indemnification

Indemnification by the Contractor

The Contractor shall indemnify the Purchaser and all parties for whom the Purchaser is responsible against any and all claims that may arise in connection with performance of the Contract, relating to:

- personal injury or loss or human life among employees of the Contractor or its subcontractors,

- loss of or damage to Provided Items after they have been delivered to the Contractor or a party for whom the Contractor is responsible, and

- any form of pollution or environmental damage.

This shall apply without regard to matters giving rise to any form of liability on the part of the Purchaser or any party for whom the Purchaser is responsible.

Indemnification by the Purchaser

The Purchaser shall indemnify the Contractor and all parties for whom the Contractor is responsible against any and all claims that may arise in connection with performance of the Contract until the time of delivery of the Scope of Delivery, relating to:

- personal injury or loss or human life among employees of the Purchaser or a party for whom the Purchaser is responsible,

- loss of or damage to property belonging to the Purchaser or a party for whom the Purchaser is responsible, except Provided Items covered by 19.1(c)

This shall apply without regard to matters giving rise to any form of liability on the part of the Contractor or its contractors.

Notification of claims

Each Party shall notify the other Party immediately of any claims that could form the basis for indemnification as mentioned in this provision.

Purchaser’s right of cancellation

The Purchaser is entitled to cancel the Contract in whole or in part by notifying the Contractor in writing if reasonable grounds exist. The notice must state the grounds for the cancellation, information about the further procedure, and state the date when the cancellation will take effect.

The Purchaser shall cover documented costs incurred in connection with the work performed, materials and administration. The Purchaser shall also cover any loss of profit relating to the Contract that the Contractor has suffered as a result of the cancellation. Cost control shall be carried out in accordance with Clause 12 Cost control.

If the Contractor fails to take reasonable steps to limit the costs resulting from the cancellation, the final settlement amount shall be reduced correspondingly.

The amount to be paid shall, under any circumstances, not exceed the contract price.

The Purchaser is entitled to receive the results of the work already carried out.

Force majeure

General information

If an extraordinary situation that is beyond the Parties’ control arises and prevents the Parties from fulfilling their obligations under the Contract, and that under Norwegian law must be considered to be a force majeure situation, the other Party shall give notice in writing as soon as possible.

If one Party fails to inform the other Party of the force majeure situation without undue delay, that Party shall forfeit its right to claim that fulfilment of the obligation was prevented by a force majeure situation.

The Parties’ obligations are suspended for the duration of the extraordinary situation.

Neither Party shall be deemed to be in breach of any obligation under the Contract if and to the extent that the Party can substantiate that fulfilment of the obligation was prevented by force majeure.

Impact on costs and schedule

Each Party shall cover its own costs resulting from the force majeure situation, and force majeure shall not affect the contract price.

After the force majeure situation has ended, the Contractor shall submit any claim for adjustment of the delivery time without undue delay. Such notification shall include an estimate of the changes to the delivery time. If the Contractor fails to comply with this, it shall not be entitled to an adjustment of the delivery time.

Cancellation for convenience

If a force majeure situation persists for more than 90 calendar days, or if the Party invoking force majeure can substantiate that it will persist for a longer period, either Party may cancel the Contract as regards the parts affected by the force majeure situation.

Miscellaneous provisions

Communication

Communication relating to this Contract shall be in writing and take place in English or Norwegian.

All correspondence shall state the contract number, and shall be sent to the persons specified in Annex D Points of Contact.

Duty to provide information

The Contractor shall notify the Purchaser in writing of matters that must be assumed to be of importance to the relationship between the Parties or the performance of the Contract, such as material changes in ownership structure, management, accounting principles and auditing firm, financial matters, damage/injuries and accidents, health, safety and the environment, and any unlawful matters.

If the Parties have signed a security agreement, the duty to provide information stipulated therein shall also be fulfilled.

Visiting procedures

The Contractor is obliged to comply with the Purchaser’s visiting procedures in connection with visits to the defence sector’s facilities.

Insurance

Materiel and documentation in accordance with the Contract shall be covered by the Contractor’s full value insurance until the risk has been transferred to the Purchaser. The Contractor’s insurance policies shall also cover the Contractor’s liability for material damage and personal injury pursuant to Clause 19 Indemnification. If the Contractor has insufficient insurance coverage, it must notify the Purchaser without undue delay. No insurance shall be taken out in favour of the Purchaser, but the insurers in the Contractor’s insurance policies shall waive any right of recourse against the Purchaser.

The Contractor shall present insurance certificates at the Purchaser’s request.

Transfer of claims

The Contractor may not assign any outstanding claims under the Contract to a third party without the Purchaser’s prior written consent. The Contractor shall remain liable for all its obligations under the Contract even if the Purchaser has given such consent.

Disputes and choice of law

The Contract shall be governed by Norwegian law.

Endeavours shall be made to resolve any disputes arising in connection with the Contract through negotiations between the Parties.

If such negotiations fail to resolve the dispute, either Party may bring the case before the courts, with Oslo District Court as the legal venue.

The fact that a dispute has been brought before the courts does not in itself relieve the Parties of their obligations under the Contract.

Entry into force

The Contract enters into force on the day when both Parties have signed the Contract.

***