Airport Work Management

Appendix 3

Plan for the establishment phase

# Appendix 3: Plan for the establishment phase

This Appendix sets out the required establishment plans for the initial deliveries and optional airport concepts under the Agreement. Please see SSA-L Appendix 1 Customer specification of requirements for more information about the airport concepts. The Supplier shall describe how it intends to plan, organise and implement each relevant delivery in accordance with the structure and milestone tables below.

The Supplier will be evaluated on its ability to present an effective, realistic and well-planned implementation approach for the establishment phase, including the proposed plan, key milestones, dependencies, risk-reducing measures, governance model and the competence and experience of the personnel proposed for the delivery. Airport Concepts A and B will form the primary basis for the evaluation. The establishment plans for Optional Airport Concepts C–E shall also be completed by the Supplier and will be evaluated under a separate sub-criterion with a lower weighting.

Delivery 1 comprises Airport Concept A at OSL. Delivery 1 shall be delivered in accordance with the milestone plan for Airport Concept A (OSL) below. The date for contract signing in the table (ID 0) is tentative. If the date for contract signing in ID 0 is changed, the other dates in the table will be changed accordingly. The dates in ID3, ID5, ID6 and ID7 shall not be changed, and the Supplier shall describe how it intends to meet these milestone deadlines.

Delivery 2 comprises Airport Concept B. Delivery 2 may be triggered by the Customer within the first three years of the Agreement. No specific calendar dates have been set for Delivery 2 at this stage. The Supplier shall therefore provide a realistic establishment plan for Airport Concept B, including estimated time periods, durations, dependencies and assumptions for the relevant activities and milestones.

Airport Concepts C–E are options under the Agreement. These options may be triggered separately for each individual airport within the relevant airport concept. No plan has been set for whether or when these options will be triggered. The Supplier shall therefore provide an overall implementation approach for each of Airport Concepts C–E, describing how the Supplier would plan and perform the establishment phase if one or more such options are exercised.

The Supplier shall submit one establishment plan for each airport concept (A–E). The plans for Airport Concepts B–E shall demonstrate how the Supplier intends to scale, adapt and implement the solution if and when the relevant delivery or option is triggered. If such delivery or option is triggered, the corresponding establishment plan submitted by the Supplier shall form the basis for the Supplier’s delivery obligations, subject to any further agreement between the parties.

For Delivery 1, go-live is desired in primo September 2027 at OSL (Airport Concept A). The Supplier shall describe how it plans to meet the project timeline, and what measures will be taken to minimise the risk of delays and cost increases.

The order of the milestones listed in the tables may change, and it is desirable that the Supplier proposes a suitable sequence and any additional milestones that should be considered for each relevant delivery or option.

Delivery 1 – Milestone Plan for Airport Concept A (OSL):

| ID | Milestone | Reference to Agreement | Date/ Time period |
| --- | --- | --- | --- |
| 0 | Contract Signing |  | [Supplier’s response] |
| 1 | Project kick-off |  | [Supplier’s response] |
| 2 | The Customer has approved the plan for the Establishment Phase | Point 3.1 | [Supplier’s response] |
| 3 | The Supplier has configured and established the system for the Customer |  | Primo Q2 2027 [Supplier’s response] |
| 4 | The Supplier has completed a full test/verification of the system |  | [Supplier’s response] |
| 5 | The Customer has received written notification (Delivery Notice) that the solution is available for the Customer's approval test. * | Point 3.2 | Ultimo July 2027 [Supplier’s response] |
| 6 | Approval test (period of up to 30 days from the first working day after the Supplier has sent the Delivery Notice) | Point 3.3 | Ultimo August 2027 [Supplier’s response] |
| 7 | Necessary training of the Customer has been completed as required in the training section * |  | Ultimo August 2027 [Supplier’s response] |
| 8 | Approval period has expired, and the Customer has sent a message that the delivery is approved (Delivery Day). * | Point 3.3 |  |

*Milestone with liquidated damages.

Delivery 2 – Milestone Plan for Airport Concept B:

| ID | Milestone | Reference to Agreement | Date/ Time period |
| --- | --- | --- | --- |
| 0 | Contract Signing |  | [Supplier’s response] |
| 1 | Project kick-off |  | [Supplier’s response] |
| 2 | The Customer has approved the plan for the Establishment Phase | Point 3.1 | [Supplier’s response] |
| 3 | The Supplier has configured and established the system for the Customer |  | [Supplier’s response] |
| 4 | The Supplier has completed a full test/verification of the system |  | [Supplier’s response] |
| 5 | The Customer has received written notification (Delivery Notice) that the solution is available for the Customer's approval test. * | Point 3.2 | [Supplier’s response] |
| 6 | Approval test (period of up to 30 days from the first working day after the Supplier has sent the Delivery Notice) | Point 3.3 | [Supplier’s response] |
| 7 | Necessary training of the Customer has been completed as required in the training section |  | [Supplier’s response] |
| 8 | Approval period has expired, and the Customer has sent a message that the delivery is approved (Delivery Day) * | Point 3.3 |  |

*Milestone with liquidated damages.

Optional Airport Concepts:

Airport Concepts C–E are options under the Agreement. There is uncertainty as to which, if any, of these options will be triggered, and when such options may be exercised. The Supplier shall therefore provide an overall establishment plan for each of Airport Concepts C–E, based on the same milestone structure as for the other airport concepts.

When preparing the plans, the Supplier shall base each plan on one airport within the relevant airport concept. Each plan shall describe the Supplier’s proposed approach, main activities, dependencies, resource assumptions and estimated time periods for the establishment phase if the relevant option is exercised.

The Supplier shall also specify the expected time period from the Customer’s exercise of the option until the establishment plan is initiated.

Optional – Milestone Plan for Airport Concept C:

| ID | Milestone | Reference to Agreement | Date/ Time period |
| --- | --- | --- | --- |
| 0 | Initiating option |  | [Supplier’s response] |
| 1 | Project kick-off |  | [Supplier’s response] |
| 2 | The Customer has approved the plan for the Establishment Phase | Point 3.1 | [Supplier’s response] |
| 3 | The Supplier has configured and established the system for the Customer |  | [Supplier’s response] |
| 4 | The Supplier has completed a full test/verification of the system |  | [Supplier’s response] |
| 5 | The Customer has received written notification (Delivery Notice) that the solution is available for the Customer's approval test. * | Point 3.2 | [Supplier’s response] |
| 6 | Approval test (period of up to 30 days from the first working day after the Supplier has sent the Delivery Notice) | Point 3.3 | [Supplier’s response] |
| 7 | Necessary training of the Customer has been completed as required in the training section |  | [Supplier’s response] |
| 8 | Approval period has expired, and the Customer has sent a message that the delivery is approved (Delivery Day) * | Point 3.3 |  |

*Milestone with liquidated damages.

Optional – Milestone Plan for Airport Concept D:

| ID | Milestone | Reference to Agreement | Date/ Time period |
| --- | --- | --- | --- |
| 0 | Initiating option |  | [Supplier’s response] |
| 1 | Project kick-off |  | [Supplier’s response] |
| 2 | The Customer has approved the plan for the Establishment Phase | Point 3.1 | [Supplier’s response] |
| 3 | The Supplier has configured and established the system for the Customer |  | [Supplier’s response] |
| 4 | The Supplier has completed a full test/verification of the system |  | [Supplier’s response] |
| 5 | The Customer has received written notification (Delivery Notice) that the solution is available for the Customer's approval test. * | Point 3.2 | [Supplier’s response] |
| 6 | Approval test (period of up to 30 days from the first working day after the Supplier has sent the Delivery Notice) | Point 3.3 | [Supplier’s response] |
| 7 | Necessary training of the Customer has been completed as required in the training section |  | [Supplier’s response] |
| 8 | Approval period has expired, and the Customer has sent a message that the delivery is approved (Delivery Day) * | Point 3.3 |  |

*Milestone with liquidated damages.

Optional – Milestone Plan for Airport Concept E:

| ID | Milestone | Reference to Agreement | Date/ Time period |
| --- | --- | --- | --- |
| 0 | Initiating option |  | [Supplier’s response] |
| 1 | Project kick-off |  | [Supplier’s response] |
| 2 | The Customer has approved the plan for the Establishment Phase | Point 3.1 | [Supplier’s response] |
| 3 | The Supplier has configured and established the system for the Customer |  | [Supplier’s response] |
| 4 | The Supplier has completed a full test/verification of the system |  | [Supplier’s response] |
| 5 | The Customer has received written notification (Delivery Notice) that the solution is available for the Customer's approval test. * | Point 3.2 | [Supplier’s response] |
| 6 | Approval test (period of up to 30 days from the first working day after the Supplier has sent the Delivery Notice) | Point 3.3 | [Supplier’s response] |
| 7 | Necessary training of the Customer has been completed as required in the training section. |  | [Supplier’s response] |
| 8 | Approval period has expired, and the Customer has sent a message that the delivery is approved (Delivery Day) * | Point 3.3 |  |

*Milestone with liquidated damages.

## Clause 3.1 of the Agreement Plan for the establishment phase

The Supplier shall describe their plan for the establishment phase (the Supplier can respond directly in this Appendix 3 or attach their response in an attachment clearly marked “Description of the establishment phase” as an attachment to this Appendix 3).

Evaluation requirements for the plan for the establishment:

- The Supplier shall outline a detailed plan for the establishment phase consisting of the different phases/milestones with activities (from the table above).

- The plan shall also describe the scope of personnel needed from both the Supplier and the Customer, and necessary capacity, roles and competence from each party. See also requirements to the establishment phase in the Agreement (General Terms and Conditions) clause 3.1.

- The Supplier shall describe the potential preparation work the Customer needs to carry out before the work with the establishment phase and the Supplier’s test/verification of the service can start.

- The Supplier shall propose an applicable meeting structure for the establishment phase.

- Additionally, the plan should clearly indicate which areas the Supplier can deliver on, as well as areas where the Supplier lacks the expertise, capacity, or ability to deliver.

[Supplier’s response]

The parties shall jointly plan and execute the transition from implementation to production (go-live) and subsequent service operations.

Go-live shall only take place after a formal Go-live decision has been approved in writing by the Customer’s Representative.

Prior to go-live, the following minimum conditions shall be fulfilled unless otherwise agreed in writing:

- agreed acceptance criteria have been successfully verified

- all critical defects have been resolved or accepted by the Customer

- required testing has been completed, including system testing, integration testing and acceptance testing

- operational procedures and documentation have been completed and approved

- training of relevant Customer personnel has been completed

- required environments, integrations and infrastructure are established and verified

- support organization and escalation paths are in place

The Supplier shall support the go-live process, including preparation, execution and immediate follow-up, and shall ensure availability of relevant key personnel during go-live and the initial stabilization period.

Following go-live, a stabilization period shall apply as agreed between the parties. During this period:

- incidents and errors shall be prioritized and resolved without undue delay

- frequent status reporting may be required

- additional support resources may be required from the Supplier

The transition to ordinary service operation (steady state) shall be formally confirmed by the Customer when the solution is considered stable and the agreed service levels can be met.

Any deviations from the agreed go-live criteria or stabilization requirements shall be documented and handled in accordance with the agreed change control procedure.

Go-live shall not be approved if unresolved issues may impact safety, security, regulatory compliance or operational continuity.

The Customer shall ensure timely availability of resources, decisions, access, data and infrastructure required for the Supplier to fulfil its obligations under the Agreement.

Any delays caused by the Customer’s failure to fulfil such obligations shall be handled in accordance with the agreed change control procedure.

The parties shall ensure that the planning and execution of the delivery takes into account operational continuity requirements, including fallback procedures where relevant.

The parties shall act in good faith and collaborate in a proactive manner to ensure efficient execution of the Agreement.

Governance and Roles

The Supplier shall provide information describing the roles available for the establishment phase of the project. Please include CVs highlighting relevant competence and experience for the key personnel. The Supplier shall also indicate the availability of the proposed resources during the establishment phase, stated as a percentage.

The Supplier shall include any additional junior and senior resources that the Supplier considers relevant for the performance of the delivery. For each proposed resource, the Supplier shall briefly describe the role, relevant competence and experience, and expected contribution to the establishment phase.

[Supplier’s response]

Roles:

- Project Manager:

The Supplier shall assign a dedicated Project Manager responsible for the overall planning, coordination, and execution of the implementation.

The Project Manager shall ensure that the delivery is carried out in accordance with the agreed scope, milestones, quality requirements, and schedule as set out in the Agreement and the Statement of Work.

This includes responsibility for establishing and maintaining a detailed project plan, coordinating resources, managing dependencies and risks, and reporting progress and deviations to the Customer.

The Project Manager shall act as the primary point of contact towards the Customer for all matters related to the implementation.

| Contact information |  |
| --- | --- |
| Name: | [Supplier’s response] |
| Position: | [Supplier’s response] |

- Test Manager

The Supplier shall assign a dedicated Test Manager responsible for planning, coordinating, and executing all test activities related to the delivery.

The Test Manager shall establish and maintain a comprehensive test strategy and test plan, including scope, approach, environments, resources, and schedule, in alignment with the Agreement and the Statement of Work.

The Test Manager shall ensure that all relevant test phases (including system testing, integration testing, and support to acceptance testing) are executed in accordance with agreed requirements, quality criteria, and timelines.

The Test Manager shall coordinate test activities across the Supplier’s team and ensure alignment with the Customer’s test processes and participation where applicable.

The Test Manager shall ensure proper defect management, including registration, prioritisation, follow-up, and resolution of defects.

The Test Manager shall establish and maintain relevant test documentation, including test cases, test results, defect reports, and test summary reports.

The Test Manager shall report test progress, risks, and deviations to the Customer, and ensure transparency on quality status throughout the implementation.

The Test Manager shall ensure that agreed entry and exit criteria for test phases are fulfilled prior to progression.

| Contact information |  |
| --- | --- |
| Name: | [Supplier’s response] |
| Position: | [Supplier’s response] |

- Business Consultant

The Supplier shall assign one or more Business Consultants responsible for analysing, detailing, and translating the Customer’s business needs into functional requirements and solution design.

The Business Consultant shall facilitate workshops and collaborate closely with the Customer to capture, clarify, and document business processes, requirements, and use cases.

The Business Consultant shall ensure that the proposed solution aligns with the Customer’s operational needs, regulatory requirements, and agreed scope as defined in the Agreement and the Statement of Work.

The Business Consultant shall contribute to the configuration and functional design of the solution, ensuring traceability from requirements through to implementation and testing.

The Business Consultant shall support the preparation of functional specifications, process descriptions, and acceptance criteria.

The Business Consultant shall assist in change management activities, including impact assessments of requirement changes and maintaining requirement traceability.

The Business Consultant shall support testing activities, including validation of requirements, review of test cases, and participation in acceptance testing where relevant.

The Business Consultant shall act as a key interface between the Customer’s business representatives and the Supplier’s technical resources to ensure correct and complete delivery.

| Contact information |  |
| --- | --- |
| Name: | [Supplier’s response] |
| Position: | [Supplier’s response] |

- Training Manager

The Supplier shall assign a dedicated Training Manager responsible for planning, coordinating, and executing all training activities related to the delivery.

The Training Manager shall establish and maintain a comprehensive training plan, including scope, target groups, training methods, materials, schedule, and required resources, in accordance with the Agreement and the Statement of Work.

The Training Manager shall ensure that training is adapted to the Customer’s operational context and user needs, including different user roles and competence levels.

The Training Manager shall develop and maintain relevant training materials, including user guides, manuals, e-learning content, and supporting documentation.

The Training Manager shall conduct or coordinate training sessions (e.g. instructor-led training, workshops, and/or digital training) and ensure that training is completed prior to system go-live.

The Training Manager shall ensure knowledge transfer to the Customer’s organisation, including super users and support functions, to enable effective adoption and operation of the solution.

The Training Manager shall evaluate training effectiveness and implement necessary improvements, including collection of feedback and documentation of training results.

The Training Manager shall coordinate training activities with the Customer and ensure alignment with the overall project plan, including dependencies to testing, acceptance, and deployment.

| Contact information |  |
| --- | --- |
| Name: | [Supplier’s response] |
| Position: | [Supplier’s response] |

- Service Manager

The Supplier shall assign a dedicated Service Manager responsible for ensuring that all delivered services comply with the agreed Service Level Agreement (SLA).

The Service Manager shall ensure that the service is delivered in a secure, stable, and reliable manner, meeting agreed availability, uptime, and performance requirements.

The Service Manager shall monitor, measure, and report service performance against agreed service levels, including availability, response times, and resolution times.

The Service Manager shall ensure effective incident and problem management, including timely handling, prioritisation, escalation, and resolution of incidents.

The Service Manager shall be responsible for root cause analysis of major incidents and implementation of corrective and preventive measures.

The Service Manager shall ensure that all service requests, incidents, and changes are tracked and handled in accordance with agreed processes.

The Service Manager shall act as the primary point of contact for all SLA-related matters and maintain regular service review meetings with the Customer.

The Service Manager shall ensure continuous improvement of the service, including identification of improvement measures and follow-up of agreed actions.

The Service Manager shall ensure that any subcontractors or third-party services comply with the agreed SLA requirements.

| Contact information |  |
| --- | --- |
| Name: | [Supplier’s response] |
| Position: | [Supplier’s response] |

The steering committee in the establishment phase shall consist of personnel from both parties, and will be responsible for monitoring the contract, tracking project progress, and serving as the decision-making body for escalating project issues and challenges. The Customer will appoint relevant representatives to the steering committee.

The Supplier is requested to specify which individuals are proposed for the steering committee, including their title and business area.

[Supplier’s response]

The establishment phase shall be performed by the key personnel listed above. Potential replacement personnel shall have the same competence as the previous personnel.

Potential change in the key personnel shall be given by the Supplier in writing, if possible, with 2 weeks’ notice. Potential changes in key personnel shall be carried out in a way that ensures minimal impact on the establishment phase. Potential cost related to changes in key personnel shall be covered by the Supplier.

## Clause 3.2 of the Agreement Delivery deadline and delivery notification

The deadline for when the service will be made available shall be specified here prior to contract signing.

## Clause 3.3 of the Agreement Approval testing and delivery day

The Customer must examine the service for a period of up to 30 (thirty) business days from the first business day after the Supplier has sent the delivery notification to the Customer (approval test).

## The Agreement’s clause 3.4 Documentation and training

The documentation must be provided no later than 14 days prior to the approval test, so that the training sessions can be conducted in the days leading up to the approval test.

The Supplier must provide a detailed description of training offered as part of the fixed price in “Appendix 6 Attachment 1 – Price form” under section “1. Establishment phase” and row 12 “Training and support during the establishment phase”. This should include:

- Who will receive the training offered

- When this training will be conducted as part of the project plan and milestones

- Details about the training offered

- Who will be responsible for providing the training material and conducting the training

- If there are any restrictions on how many people can receive the training, and if so, how many

- If the training should be delivered digitally or with physical presence

- Overview of the training material/documentation that will be available for Avinor before and/or after the received training

In addition, any training outside of the fixed price training offered above that the Supplier can provide for Avinor should be outlined in an additional overview with included optional pricing and with the same detailing as the bullet points above.

The above can be, if necessary, delivered as an attachment to Appendix 3.

[Supplier’s response]

## Clause 9.2.3 of the Agreement Liquidated damages in the event of delay

The liquidated damages amount to 0.15 per cent of the agreed consideration payable for the payment milestone 2 and 3 in SSA-L Appendix 6 Total price and pricing provisions (respectively 30% and 60% of the total cost for the establishment phase for each Airport Concept).