## Document Plan
Document number | Document name Document Plan Type 73 toilet wastetanks | Rev. number | NT documents to be updated | Tender | FDR | Start Serial production | End Serial production
| Document plan "Type 73 toilet wastetanks." (This document) |  |  | 1st version | 2nd version |  | 3rd version
| Document delivery plan (detailed) |  |  |  | 1st version |  | Final
| Declaration of Conformity Type 73 |  |  | 1st version | Final
| Fire Technical Compliance for All System Components EN45545 |  |  | 1st version | Final
| Components List (Apparatliste) |  |  |  | 1st version |  | Final
| Design documents |  |  | 1st version | 2nd version |  | Final
| Product descriptions |  |  |  | 1st version |  | Final
| Weight calculations |  |  | 1st version | 2nd version |  | Final
| Manufacturing drawings 2D |  |  |  | 1st version |  | Final
| Data sheets and certificates for all parts and components |  |  |  | 1st version |  | Final
| Test and inspection documentation |  |  |  | 1st version |  | Final
| Desctription of manufacturing processes and calculations |  |  |  | 1st version | 2nd version | Final
| Bill of Materials |  |  |  | 1st version | 2nd version | Final

## Revision history
Rev | Rev dato | Kommentar | Sign
01 | 2025-11-28 | Nytt dokument | JG