## Revision history
Rev | Rev dato | Kommentar | Sign
01 | 2025-12-08 | Nytt dokument | AGB

## Document Plan
Document number | Document name Document Plan Class 5 | Rev. number | NT documents to be updated | Tender | FDR | Start Serial production | FOC | End Serial production
| Document Plan Class 5 Interior lights LED.xlsx (This document) |  |  | 1st version | 2nd version |  |  | 3rd version
| Document delivery plan (detailed) |  |  |  | 1st version |  |  | Final
Project schedule
| Declaration of Conformity Class 5 - prototype installation |  |  |  | Final
| Declaration of Conformity Class 5 - serial installation (for all serial vehicles) | [6 empty] | Final
| RCM Analysis information for update |  |  |  | 1st version |  | Final
| Codification of Components EN15380-2 |  |  |  | 1st version | Final
| Fire Technical Compliance for All System Components EN45545 |  |  |  | Final
| Software Package and License |  |  |  |  | Final
| User Manual for Software Version | [5 empty] | Final
| Components List (Apparatliste) |  |  |  | 1st version |  | Final
| Cable List (Kabelliste) |  |  |  | 1st version |  | Final
| Design documents |  |  | 1st version | Final
| System descriptions |  |  | 1st version | Final
| Product descriptions |  |  |  | 1st version |  | Final
| Operating instructions |  |  |  | 1st version |  | Final
| System schematics |  |  |  | 1st version |  | Final
| Weight calculations |  |  | 1st version | Final
| Assembly drawings 2D |  |  |  | 1st version |  | Final
| Detail drawings 2D |  |  |  | 1st version |  | Final
| Parts lists |  |  |  | 1st version |  | Final
| Data sheets for all parts and components |  |  |  | 1st version |  | Final
| Illustrated parts catalogue – IPC |  |  |  | 1st version |  | Final
| Test documentation |  |  |  | 1st version |  |  | Final
| Detailed installation instructions |  |  |  | 1st version | Final
| List of removed articles and components | [5 empty] | 1st version | Final
| Bill of Materials |  |  |  | 1st version | Final
| Commissioning documentation FOC | [5 empty] | Final
| Commissioning documentation Serial | [6 empty] | Final
| Maintenance documentation with illustrations |  |  |  | 1st version |  | Final
| Uninstalling and installing documentation |  |  |  | 1st version |  | Final
| Spare Parts Analysis and Price Specification |  |  |  | 1st version |  | Final
| Software maintenance documentation for all Components |  |  |  | 1st version |  | Final
| Documentation of data connections (VLAN, VPN, Firewall Configuration) and interfaces |  |  |  | 1st version |  | Final