## Payment plan
Total price in NOK
| Payment plan | Percentage of total price invoiced for each milestone | Payment
Milestone 1 | Sub-system design and productionization readiness (end of week 6, expected) – this should include sharing of initial versions of production designs of all the sub-systems and discussion on whether they meet the design and function expectations | 20% | 0
Milestone 2 | Rev 1 prototypes delivery (end of month 3, expected) – this is marked by UiT receiving 2 Rev 1 prototypes and performing a first successful run on-site. | 50% | 0
Milestone 3 | End of the project – this is marked by delivery of all the deliverables and performing a first successful run onsite, and UiT assessing all the deliverables as acceptable | 30% | 0
Please state total price in cell D5, including all relevant costs, excluding VAT. Currency is NOK
There is no oppurtunity to invoice more than total price over the course of contract
Maximum budget for the procurement is 3 300 000 NOK. Ex. VAT