## Revision history
Rev | Rev date | Comment | Sign
01 | 2025-12-08 | Nytt dokument | AGB
2 | 2026-09-02 | Adjusted for T71 T72 | RAN

## Document Plan
Document number | Document name Document Plan Class 5 | Rev. number | NT documents to be updated | Tender | First Design Review | FDR Final Design Review | Delivery of prototype | Delivery of prototype2 | Delivery of components/ parts
| Document Plan T71 T73AB Interior lights LED.xlsx (This document) |  |  | 1st version |  | 2nd version |  | 3rd version
| Document delivery plan (detailed) |  |  |  |  | 1st version |  | Final
| Project schedule |  |  | 1st version
| Declaration of Conformity T71 T73AB- prototype installation |  |  |  |  | Final
| Declaration of Conformity T71 T73AB- serial installation (for all serial vehicles) | [6 empty] | Final
| RCM Analysis information for update |  |  |  |  | 1st version |  | Final
| Codification of Components EN15380-2 |  |  |  |  | 1st version |  | Final
| Fire Technical Compliance for All System Components EN45545 |  |  |  | 1st version | Final
| Software Package and License | [6 empty] | Final
| User Manual for Software Version | [6 empty] | Final
| Components List (Apparatliste) |  |  |  | 1st version | 2nd version |  | Final
| Cable List (Kabelliste) |  |  |  | 1st version | 2nd version |  | Final
| Design documents |  |  | 1st version |  | Final
| System descriptions |  |  | 1st version |  | Final
| Product descriptions |  |  |  |  | 1st version |  | Final
| Operating instructions |  |  |  |  | 1st version |  | Final
| System schematics |  |  |  |  | 1st version |  | Final
| Weight calculations |  |  | 1st version |  | Final
| Assembly drawings 2D |  |  |  | 1st version |  |  | Final
| Detail drawings 2D |  |  |  |  | 1st version |  | Final
| Parts lists |  |  |  | 1st version | 2nd version |  | Final
| Data sheets for all parts and components |  |  |  |  | 1st version |  | Final
| Illustrated parts catalogue – IPC |  |  |  |  | 1st version |  | Final
| Test documentation |  |  |  | 1st version | 2nd version |  | Final
| Detailed installation instructions |  |  |  |  | 1st version |  | Final
| List of removed articles and components |  |  |  |  | 1st version |  | Final
| Bill of Materials |  |  | 1st version | 2nd version |  |  | Final
| Commissioning documentation FOC |  |  |  |  | 1st version |  | Final
| Commissioning documentation Serial |  |  |  | 1st version | 2nd version |  | Final
| Maintenance documentation with illustrations |  |  |  |  | 1st version |  | Final
| Uninstalling and installing documentation |  |  |  | 1st version | 2nd version |  | Final
| Spare Parts Analysis and Price Specification |  |  | 1st version |  | 2nd version |  | Final
| Software maintenance documentation for all Components (If applicable) |  |  |  |  | 1st version |  | Final
| LCC values |  |  |  |  | 1st version |  | Final
| Documentation of data connections (VLAN, VPN, Firewall Configuration) and interfaces (If applicable) |  |  |  |  | 1st version |  | Final